## Civil
Civil Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 20 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
CIV-PS3-DRN-001 | CIV-PS3-DRN-001-01 | Stormwater drainage channel installation Section A | m | 120 | 90 | 20 | 110 |  | Invert elevation checked against benchmark
Report summary | Value |  | Site conditions | Value
Total activities | 1 |  | Weather | Good working conditions

## Piping
Piping Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 20 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
PIP-PS3-HDR-100-B | PIP-PS3-HDR-100-B-01 | Utility header spool Section B fit-up and erection | m | 30 | 18 | 7 | 25 |  | Flange alignment accepted
Report summary | Value |  | Site conditions | Value
Total activities | 1 |  | Weather | Good working conditions

## Electrical
Electrical Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 20 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
ELE-PS3-TR-005 | ELE-PS3-TR-005-01 | Cable tray installation Main Piperack Tier 2 | m | 200 | 90 | 50 | 140 |  | Tier 2 tray run complete to grid line 4
Report summary | Value |  | Site conditions | Value
Total activities | 1 |  | Weather | Good working conditions