## Civil
Civil Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 16 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
CIV-PS3-DRN-001 | CIV-PS3-DRN-001-01 | Stormwater Drainage Channel Installation | m | 120 | 60 | 30 | 90 | 75 | Channel lining progressing on schedule
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Clear, light breeze |  | Daily report | daily_progress_report_2026-08-16.txt
Current physical progress | 75 |  | Manpower | 19 |  | Diary scan | site_diary_2026-08-16.jpg

## Piping
Piping Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 16 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
PIP-PS3-HDR-100-B | PIP-PS3-HDR-100-B-01 | Utility Header Spool Section B fabrication | m | 30 | 10 | 10 | 20 | 66.6667 | Spool fit-up verified before weld-out
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Clear, light breeze |  | Daily report | daily_progress_report_2026-08-16.txt
Current physical progress | 66.6667 |  | Manpower | 19 |  | Diary scan | site_diary_2026-08-16.jpg

## Electrical
Electrical Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 16 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
ELE-PS3-CT-012 | ELE-PS3-CT-012-01 | Cable trench bedding at MCC-01 | m | 140 | 95 | 25 | 120 | 85.7143 | Bedding sand compacted to spec
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Clear, light breeze |  | Daily report | daily_progress_report_2026-08-16.txt
Current physical progress | 85.7143 |  | Manpower | 19 |  | Diary scan | site_diary_2026-08-16.jpg

## Instrumentation
Instrumentation Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 16 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
INS-PS3-ITR-002 | INS-PS3-ITR-002-01 | Instrument cable tray installation at PR-01 | m | 180 | 100 | 30 | 130 | 72.2222 | Tray supports aligned per drawing
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Clear, light breeze |  | Daily report | daily_progress_report_2026-08-16.txt
Current physical progress | 72.2222 |  | Manpower | 19 |  | Diary scan | site_diary_2026-08-16.jpg

## HSE
HSE Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 16 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
HSE-PS3-BAR-002 | HSE-PS3-BAR-002-01 | Deep excavation hard barricading | m | 300 | 270 | 30 | 300 | 100 | Full barricade run closed out and inspected
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Clear, light breeze |  | Daily report | daily_progress_report_2026-08-16.txt
Current physical progress | 100 |  | Manpower | 19 |  | Diary scan | site_diary_2026-08-16.jpg