## Civil
Civil Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 17 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
CIV-PS3-BKF-001 | CIV-PS3-BKF-001-01 | Trench backfill and compaction CH 0+000-0+180 | m3 | 350 | 90 | 60 | 150 | 42.8571 | Compaction test results pending lab confirmation
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Overcast, no rain |  | Daily report | daily_progress_report_2026-08-17.txt
Current physical progress | 42.8571 |  | Manpower | 20 |  | Diary scan | site_diary_2026-08-17.jpg

## Piping
Piping Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 17 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
PIP-PS3-SPT-030 | PIP-PS3-SPT-030-01 | Pipe support secondary steel erection | ea | 100 | 40 | 15 | 55 | 55 | Supports erected on Rack PR-02 span
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Overcast, no rain |  | Daily report | daily_progress_report_2026-08-17.txt
Current physical progress | 55 |  | Manpower | 20 |  | Diary scan | site_diary_2026-08-17.jpg

## Electrical
Electrical Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 17 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
ELE-PS3-TR-005 | ELE-PS3-TR-005-01 | Cable tray installation Piperack Tier 2 | m | 200 | 65 | 35 | 100 | 50 | Tray splice joints torque-checked
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Overcast, no rain |  | Daily report | daily_progress_report_2026-08-17.txt
Current physical progress | 50 |  | Manpower | 20 |  | Diary scan | site_diary_2026-08-17.jpg

## Static Rotating Equipment
Static Rotating Equipment Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 17 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
EQP-PS3-SKD-002 | EQP-PS3-SKD-002-01 | Chemical Dosing Skid SK-02 positioning | ea | 1 | 0 | 1 | 1 | 100 | Skid set on foundation and leveled
Report summary | Value |  | Site conditions | Value |  | References | File
Total activities | 1 |  | Weather | Overcast, no rain |  | Daily report | daily_progress_report_2026-08-17.txt
Current physical progress | 100 |  | Manpower | 20 |  | Diary scan | site_diary_2026-08-17.jpg