## Civil
Civil Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 18 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
CIV-PS3-FND-002 | CIV-PS3-FND-002-01 | Pump P-101/P-102 foundation rebar and shuttering | t | 12 | 4 | 8 | 12 |  | Rebar fixing inspected and approved
CIV-PS3-TR-0220 | CIV-PS3-TR-0220-01 | Utility trench excavation CH 0+220 to 0+260 | m | 40 | 20 | 20 | 40 |  | Trench depth verified along chainage
Report summary | Value |  | Site conditions | Value
Total activities | 2 |  | Weather | Good working conditions

## Piping
Piping Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 18 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
PIP-PS3-HDR-100-B | PIP-PS3-HDR-100-B-01 | Utility header spool Section B fit-up and erection | m | 30 | 0 | 10 | 10 |  | Fit-up inspection passed
Report summary | Value |  | Site conditions | Value
Total activities | 1 |  | Weather | Good working conditions

## Electrical
Electrical Daily Discipline Report
North Field Utility Corridor ¦ Pump Station 3 Tie In ¦ Report date: 18 Aug 2026
L5 Activity ID | L6 Task ID | Work description | Unit | Planned qty | Prior actual | Today actual | Cumulative actual | Progress | Status and evidence
ELE-PS3-TR-005 | ELE-PS3-TR-005-01 | Cable tray installation Main Piperack Tier 2 | m | 200 | 40 | 50 | 90 |  | Tray alignment and grounding jumper verified
Report summary | Value |  | Site conditions | Value
Total activities | 1 |  | Weather | Good working conditions